## Utils (hidden)
Member | All | Austin Nguyen | Nathan Duong | Steven Bui

## Backlog
Event Planner - CS175 Final Project
Members: | Austin Nguyen, Nathan Duong, Steven Bui
Task | Description | Member | Status | Start Date | End Date | Comments
Brainstorm | Brainstorm the plans on tackling the project | All | Completed | 2025-03-09 | 2025-03-23
Meetings | Meetings to discuss plans | All | Completed | 2025-03-16 | 2025-03-22
Setup/Research | Set up GitHub Repo and researching frameworks/libraries | All | Completed | 2025-03-23 | 2025-04-06
Setup/Research | Planned out files needed for project | All | Completed | 2025-04-06 | 2025-04-21
Implementation | Set up Events database in app | All | Completed | 2025-04-21 | 2025-04-23
Implementation | Implemented Dashboard | Nathan Duong | Completed | 2025-04-23 | 2025-05-03
Implementation | Implemented Events | Steven Bui | Completed | 2025-04-23 | 2025-05-03
Implementation | Implemented Calendar | Austin Nguyen | Completed | 2025-04-23 | 2025-05-03
Meetings | Meeting to review app + future plans | All | Completed | 2025-05-04 | 2025-05-04
Meetings | Post Peer-review meeting | All | Completed | 2025-05-06 | 2025-05-06
Implementation | Fixed Peer-review notes | All | Completed | 2025-05-06 | 2025-05-11
Implementation | Finalize Source code + testing | All | Completed | 2025-05-11 | 2025-05-12
Submission | Finish Report + README | All | Completed | 2025-05-12 | 2025-05-12
Submission | Submit Project | All | Completed | 2025-05-12 | 2025-05-12
Presentation | Prepare Presentation + Slides | All | In Progress | 2025-05-12

## Read Me
To use the template
1 | File -> Make a copy, change the document name accordingly,
and share it among the members & the instructor (yan.chen01@sjsu.edu)
2 | In Backlog, enter project name and group members
Then document each task as a row:
| 2.1) | Task name (such as Brainstorming, UI Design, etc.)
| 2.2) | Describe the task in more details
| 2.3) | Choose the member who's responsible for the task
| 2.4) | Choose the status
| 2.5) | For started (In Progress) tasks, enter the start date
| 2.6) | For Completed tasks, enter the end date
| 2.7) | Enter any additional notes
3 | Hide or Delete this Read Me Page (or Move it after Backlog so Backlog is the front page)
Color Codes (auto)
Red background: |  | Error
Red text: |  | Urgent task (due soon or blocking other tasks)
Grey text: |  | Completed
The last submission should have NO red background (no error) and all taskes should be in grey (all completed)
Possible Errors
| 2 | Missing group number or group members
| 2.5) | Missing start date for an In Progress or Completed task
OR Having start date for a Not Started task
| 2.6) | Missing end date for a Completed task
OR Having end date for an uncompleted task